## project 1
members | task | start time | end time | Specific | Measurable | Achievable | Relevant
Nuray Niyazbek , Akzhan Bazarbayeva, Mariyam Iztleuova ,Zhanerke Bolat | The main stages of system installation | 2020-10-06 | 2020-12-30 | Find mysql,linux on websites and install | installation sites found = 18 | More than 20 sciences materials related to installations | Yes, because we need to install applications
Akzhan Bazarbayeva | software design | 2020-10-08 | 2020-10-14 | create an model to visualize process | done=0 clarity=0 | Clarity can be at least 80% | it help to see our working systems
Mariyam Iztleuova ,Zhanerke Bolat | database design | 2020-10-08 | 2020-10-15 | create connection with database | done=0 clarity=0 | Clarity can be at least 80% | with it we can working with db which connected uml
Nuray Niyazbek | server of our project | 2020-10-08 | 2020-10-16 | create server ,http for Linux | clarity=0 | clarity can be at least 70% | it help for security websites and controling
Mariyam Iztleuova ,Zhanerke Bolat | mysql of our project | 2020-11-01 | 2020-11-28 | Create a database to understand where to record and store our project data | done=0 | creation db clarity should be at least 80% | Yes, because with it we are know where to store data working DWH
Akzhan Bazarbayeva,Nuray Niyazbek | administrator page | 2020-10-15 | 2020-10-25 | create a admin page to adding users | clarity=0 | clarity can be at least 80% | with admin page we are can add or remove some features
Akzhan Bazarbayeva | register form log (in/out) | 2020-10-18 | 2020-10-25 | create a register form to verification | clarity=0 | clarity can ve at least 80% | with it users can authorization to site
Akzhan Bazarbayeva,Nuray Niyazbek | account page | 2020-10-20 | 2020-10-26 | create profile users | clarity=0 | clarity can ve at least 80% | with account page we see some info of users
Mariyam Iztleuova ,Zhanerke Bolat | database | 2020-11-25 | 2020-12-26 | connect db-DL to db-Campus | clarity=0 | clarity can ve at least 80% | with it we generate some referance
Nuray Niyazbek , Akzhan Bazarbayeva, Mariyam Iztleuova ,Zhanerke Bolat | Testing and debugging | 2021-04-15 | 2021-05-31 | testing system to find and resolve debugging | clarity=0 | clarity can be at least 95% | with tesing we finish a project without fails